## Sheet1
GANTT CHART For Capstone Phase 2
PROJECT TITLE |  | Pseudocode2c
PROJECT MANAGER |  | Prof. Nitin V. Pujari
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Tasks | Start Date | Duration
[7 empty] | Definition and structure of Pseudocode | 2021-06-08 | 3
1 | Definition and structure of Pseudocode | [5 empty] | Creating Testing Dataset | 2021-06-11 | 7
1.1 | Declaring and closing the conditional Statements | All 4 | 2021-06-08 | 2021-06-10 | 2 | 100% | Implementing different approaches | 2021-06-15 | 18
1.1.1 | Declaring and cloding the Loops | All 4 | 2021-06-08 | 2021-06-10 | 2 | 100% | Finalizing one approach | 2021-07-03 | 7
[7 empty] | Mapping pseudocode to source code | 2021-09-10 | 20
[7 empty] | Integration of constructs | 2021-10-02 | 3
1.2 | Simialar words for Scanf and Printf | All 4 | 2021-06-08 | 2021-06-10 | 2 | 100% | Interface of Framework (GUI) | 2021-10-05 | 7
2 | Creating Testing Dataset | [5 empty] | Testing of framework | 2021-10-13 | 8
2.1 | Class 6 Pseudocode | Rajdeep | 2021-06-11 | 2021-06-14 | 3 | 100%
2.2 | Class 7 Pseudocode | Srishti | 2021-06-11 | 2021-06-14 | 3 | 100%
2.3 | Class 8 Pseudocode | Raghav and Shaashwat | 2021-06-11 | 2021-06-14 | 3 | 100%
3 | Mapping Pseudocode to Source Code
3.1 | XML based approach | Srishti | 2021-06-15 | 2021-07-02 | 17 | 100%
3.2 | LSTM Neural Network approach | Rajdeep | 2021-06-15 | 2021-07-02 | 17 | 100%
3.3 | Python Static Stubs approach | Shaashwat | 2021-06-15 | 2021-07-02 | 17 | 100%
3.4 | Pseudocode2c compiler | Raghav | 2021-06-15 | 2021-07-02 | 17 | 100%
4 | Finalizing one approach
4.1 | Finializing the approach which yields best results | All 4 | 2021-07-03 | 2021-07-03 | 1 | 0%
4.2 | Constructs for printing and reading | Rajdeep | 2021-07-04 | 2021-07-10 | 6 | 0%
4.3 | Constructs for Conditional Statements | Srishti | 2021-07-04 | 2021-07-10 | 6 | 0%
4.4 | Constructs for while and for | Raghav | 2021-07-04 | 2021-07-10 | 6 | 0%
4.5 | Constructs for scope and variables | Shaashwat | 2021-07-04 | 2021-07-10 | 6 | 0%
5 | Interface of Framework
5.1 | Creating the Frontend | Rajdeep and Sishti | 2021-07-11 | 2021-07-16 | 5 | 0%
5.2 | Integrating Framework with the frontend | Raghav and Shaashwat | 2021-07-11 | 2021-07-16 | 5 | 0%
6 | Testing
6.1 | Testing constructs for printing and reading | Srishti | 2021-07-16 | 2021-07-24 | 8 | 0%
6.2 | Testing constructs for Conditional Statements | Rajdeep | 2021-07-16 | 2021-07-24 | 8 | 0%
6.3 | Testing constructs for while and for | Shaashwat | 2021-07-16 | 2021-07-24 | 8 | 0%
6.4 | Testing constructs for scope and variables | Raghav | 2021-07-16 | 2021-07-24 | 8 | 0%
6.5 | Testing the whole Framework | All 4 | 2021-07-16 | 2021-07-24 | 8 | 0%